## All installs
Install date | Slot | Ref | Name | Hall | Location | Type | W (mm) | H (mm) | Qty | Fixing | Weight (kg) | Status | Contractor
2 Oct 2027 | PM | SIG-BIRM27-001 | Main entrance arch banner | Hall 1 | Main entrance | Entrance feature | 3000 | 1000 | 1 | Freestanding |  | In review | Unassigned
2 Oct 2027 | AM | SIG-BIRM27-002 | Registration desk fascia | Hall 1 | Registration | Registration | 3000 | 1000 | 1 | Freestanding |  | In review | Unassigned
2 Oct 2027 | PM | SIG-BIRM27-003 | Aisle A hanging banner | Hall 1 | Central aisle A | Hanging banner | 3000 | 1000 | 1 | Rigged |  | In review | Unassigned
2 Oct 2027 | AM | SIG-BIRM27-004 | Seminar theatre 1 backdrop | Hall 1 | Seminar theatre 1 | Seminar theatre | 3000 | 1000 | 1 | Freestanding |  | In review | Unassigned
2 Oct 2027 | PM | SIG-BIRM27-005 | Catering court floor vinyl | Hall 1 | Catering court | Floor vinyl | 3000 | 1000 | 1 | Floor |  | Changes requested | Unassigned
2 Oct 2027 | AM | SIG-BIRM27-006 | Feature area totem | Hall 1 | Feature area | Feature area | 3000 | 1000 | 1 | Freestanding |  | In review | Unassigned
2 Oct 2027 | PM | SIG-BIRM27-007 | Hall 2 entrance banner | Hall 2 | Hall 2 entrance | Hanging banner | 3000 | 1000 | 1 | Rigged |  | In review | Unassigned
2 Oct 2027 | AM | SIG-BIRM27-008 | Aisle B hanging banner | Hall 2 | Central aisle B | Aisle sign | 3000 | 1000 | 1 | Rigged |  | Approved | Unassigned
2 Oct 2027 | PM | SIG-BIRM27-009 | Seminar theatre 2 entrance sign | Hall 2 | Seminar theatre 2 | Seminar theatre | 3000 | 1000 | 1 | Freestanding |  | Approved with conditions | Unassigned
2 Oct 2027 | AM | SIG-BIRM27-010 | Networking lounge fabric wall | Hall 2 | Networking lounge | Fabric graphic | 3000 | 1000 | 1 | Shell mounted |  | In production | Unassigned
2 Oct 2027 | PM | SIG-BIRM27-011 | External approach flags | Hall 2 | External approach | External | 3000 | 1000 | 1 | Freestanding |  | In production | Unassigned
2 Oct 2027 | AM | SIG-BIRM27-012 | Link corridor wayfinding | Hall 2 | Link corridor | Foamex board | 3000 | 1000 | 1 | Wall mounted |  | Delivered | Unassigned
2 Oct 2027 | PM | SIG-BIRM27-013 | Registration totem screens | Hall 1 | Registration | Digital screen | 3000 | 1000 | 1 | Digital |  | Delivered | Unassigned
2 Oct 2027 | AM | SIG-BIRM27-014 | Hall 1 aisle signs set | Hall 1 | Central aisle A | Aisle sign | 3000 | 1000 | 1 | Rigged |  | Installed | Unassigned
2 Oct 2027 | PM | SIG-BIRM27-015 | Catering signage pack | Hall 1 | Catering court | Foamex board | 3000 | 1000 | 1 | Wall mounted |  | Snagged | Unassigned
2 Oct 2027 | AM | SIG-BIRM27-016 | Sponsor wall Hall 1 | Hall 1 | Feature area | Feature area | 3000 | 1000 | 1 | Freestanding |  | Closed | Unassigned
2 Oct 2027 | PM | SIG-BIRM27-017 | Gantry banner over aisle C | Hall 2 | Central aisle B | Hanging banner | 3000 | 1000 | 1 | Rigged |  | Rejected | Unassigned
2 Oct 2027 | AM | SIG-BIRM27-018 | VIP lounge entrance sign | Hall 2 | Networking lounge | Fabric graphic | 3000 | 1000 | 1 | Shell mounted |  | On hold | Unassigned
2 Oct 2027 | PM | SIG-BIRM27-019 | BuildCo banner — north hall | Hall 1 | Central aisle A | Hanging banner | 3000 | 1000 | 1 | Rigged |  | In review | Unassigned
2 Oct 2027 | AM | SIG-BIRM27-020 | Organiser office door signs | Hall 2 | Link corridor | Foamex board | 3000 | 1000 | 1 | Wall mounted |  | Awaiting artwork | Unassigned
2 Oct 2027 | PM | SIG-BIRM27-021 | Cloakroom signage | Hall 1 | Registration | Foamex board | 3000 | 1000 | 1 | Wall mounted |  | Awaiting artwork | Unassigned
2 Oct 2027 | AM | SIG-BIRM27-022 | Press office fascia | Hall 2 | Hall 2 entrance | Registration | 3000 | 1000 | 1 | Freestanding |  | Awaiting artwork | Unassigned
2 Oct 2027 | PM | SIG-BIRM27-023 | Hall 1 big screen content loop | Hall 1 | Feature area | Digital screen | 3000 | 1000 | 1 | Digital |  | Draft | Unassigned
2 Oct 2027 | AM | SIG-BIRM27-024 | Wayfinding floor arrows | Hall 2 | Seminar theatre 2 | Floor vinyl | 3000 | 1000 | 1 | Floor |  | Draft | Unassigned
2 Oct 2027 | PM | SIG-BIRM27-025 | ToolMart seminar bunting | Hall 2 | Seminar theatre 2 | Seminar theatre | 3000 | 1000 | 1 | Freestanding |  | Draft | Unassigned
2 Oct 2027 | AM | SIG-BIRM27-026 | External car park totems | Hall 2 | External approach | External | 3000 | 1000 | 1 | Freestanding |  | Draft | Unassigned
2 Oct 2027 | PM | SIG-BIRM27-027 | Smoking area signage | Hall 2 | External approach | Foamex board | 3000 | 1000 | 1 | Wall mounted |  | Draft | Unassigned
2 Oct 2027 | AM | SIG-BIRM27-028 | First aid point signs | Hall 1 | Catering court | Foamex board | 3000 | 1000 | 1 | Wall mounted |  | Changes requested | Unassigned
2 Oct 2027 | PM | SIG-BIRM27-029 | BuildCo entrance feature cladding | Hall 1 | Main entrance | Entrance feature | 3000 | 1000 | 1 | Freestanding |  | In review | Unassigned
2 Oct 2027 | AM | SIG-BIRM27-030 | Recycling point signage | Hall 2 | Link corridor | Foamex board | 3000 | 1000 | 1 | Wall mounted |  | Draft | Unassigned
TBC |  | SIG-BIRM27-031 | E2E test sign 1789742365412 | Hall 1 | Registration | Foamex board | 1200 | 800 | 1 | Wall mounted |  | Awaiting artwork | Unassigned
TBC |  | SIG-BIRM27-032 | E2E test sign 1789742409349 | Hall 1 | Registration | Foamex board | 1200 | 800 | 1 | Wall mounted |  | Awaiting artwork | Unassigned
TBC |  | SIG-BIRM27-033 | E2E test sign 1789742782693 | Hall 1 | Registration | Foamex board | 1200 | 800 | 1 | Wall mounted |  | Awaiting artwork | Unassigned
TBC |  | SIG-BIRM27-034 | E2E test sign 1789743854785 | Hall 1 | Registration | Foamex board | 1200 | 800 | 1 | Wall mounted |  | Awaiting artwork | Unassigned
TBC |  | SIG-BIRM27-035 | E2E test sign 1789743908499 | Hall 1 | Registration | Foamex board | 1200 | 800 | 1 | Wall mounted |  | In review | Unassigned
TBC |  | SIG-BIRM27-036 | E2E test sign 1789746737063 | Hall 1 | Registration | Foamex board | 1200 | 800 | 1 | Wall mounted |  | In review | Unassigned
TBC |  | SIG-BIRM27-037 | E2E test sign 1789747154397 | Hall 1 | Registration | Foamex board | 1200 | 800 | 1 | Wall mounted |  | In review | Unassigned
TBC |  | SIG-BIRM27-038 | E2E test sign 1789748321968 | Hall 1 | Registration | Foamex board | 1200 | 800 | 1 | Wall mounted |  | In review | Unassigned

## Unassigned
Install date | Slot | Ref | Name | Hall | Location | Type | W (mm) | H (mm) | Qty | Fixing | Weight (kg) | Status | Contractor
2 Oct 2027 | PM | SIG-BIRM27-001 | Main entrance arch banner | Hall 1 | Main entrance | Entrance feature | 3000 | 1000 | 1 | Freestanding |  | In review | Unassigned
2 Oct 2027 | AM | SIG-BIRM27-002 | Registration desk fascia | Hall 1 | Registration | Registration | 3000 | 1000 | 1 | Freestanding |  | In review | Unassigned
2 Oct 2027 | PM | SIG-BIRM27-003 | Aisle A hanging banner | Hall 1 | Central aisle A | Hanging banner | 3000 | 1000 | 1 | Rigged |  | In review | Unassigned
2 Oct 2027 | AM | SIG-BIRM27-004 | Seminar theatre 1 backdrop | Hall 1 | Seminar theatre 1 | Seminar theatre | 3000 | 1000 | 1 | Freestanding |  | In review | Unassigned
2 Oct 2027 | PM | SIG-BIRM27-005 | Catering court floor vinyl | Hall 1 | Catering court | Floor vinyl | 3000 | 1000 | 1 | Floor |  | Changes requested | Unassigned
2 Oct 2027 | AM | SIG-BIRM27-006 | Feature area totem | Hall 1 | Feature area | Feature area | 3000 | 1000 | 1 | Freestanding |  | In review | Unassigned
2 Oct 2027 | PM | SIG-BIRM27-007 | Hall 2 entrance banner | Hall 2 | Hall 2 entrance | Hanging banner | 3000 | 1000 | 1 | Rigged |  | In review | Unassigned
2 Oct 2027 | AM | SIG-BIRM27-008 | Aisle B hanging banner | Hall 2 | Central aisle B | Aisle sign | 3000 | 1000 | 1 | Rigged |  | Approved | Unassigned
2 Oct 2027 | PM | SIG-BIRM27-009 | Seminar theatre 2 entrance sign | Hall 2 | Seminar theatre 2 | Seminar theatre | 3000 | 1000 | 1 | Freestanding |  | Approved with conditions | Unassigned
2 Oct 2027 | AM | SIG-BIRM27-010 | Networking lounge fabric wall | Hall 2 | Networking lounge | Fabric graphic | 3000 | 1000 | 1 | Shell mounted |  | In production | Unassigned
2 Oct 2027 | PM | SIG-BIRM27-011 | External approach flags | Hall 2 | External approach | External | 3000 | 1000 | 1 | Freestanding |  | In production | Unassigned
2 Oct 2027 | AM | SIG-BIRM27-012 | Link corridor wayfinding | Hall 2 | Link corridor | Foamex board | 3000 | 1000 | 1 | Wall mounted |  | Delivered | Unassigned
2 Oct 2027 | PM | SIG-BIRM27-013 | Registration totem screens | Hall 1 | Registration | Digital screen | 3000 | 1000 | 1 | Digital |  | Delivered | Unassigned
2 Oct 2027 | AM | SIG-BIRM27-014 | Hall 1 aisle signs set | Hall 1 | Central aisle A | Aisle sign | 3000 | 1000 | 1 | Rigged |  | Installed | Unassigned
2 Oct 2027 | PM | SIG-BIRM27-015 | Catering signage pack | Hall 1 | Catering court | Foamex board | 3000 | 1000 | 1 | Wall mounted |  | Snagged | Unassigned
2 Oct 2027 | AM | SIG-BIRM27-016 | Sponsor wall Hall 1 | Hall 1 | Feature area | Feature area | 3000 | 1000 | 1 | Freestanding |  | Closed | Unassigned
2 Oct 2027 | PM | SIG-BIRM27-017 | Gantry banner over aisle C | Hall 2 | Central aisle B | Hanging banner | 3000 | 1000 | 1 | Rigged |  | Rejected | Unassigned
2 Oct 2027 | AM | SIG-BIRM27-018 | VIP lounge entrance sign | Hall 2 | Networking lounge | Fabric graphic | 3000 | 1000 | 1 | Shell mounted |  | On hold | Unassigned
2 Oct 2027 | PM | SIG-BIRM27-019 | BuildCo banner — north hall | Hall 1 | Central aisle A | Hanging banner | 3000 | 1000 | 1 | Rigged |  | In review | Unassigned
2 Oct 2027 | AM | SIG-BIRM27-020 | Organiser office door signs | Hall 2 | Link corridor | Foamex board | 3000 | 1000 | 1 | Wall mounted |  | Awaiting artwork | Unassigned
2 Oct 2027 | PM | SIG-BIRM27-021 | Cloakroom signage | Hall 1 | Registration | Foamex board | 3000 | 1000 | 1 | Wall mounted |  | Awaiting artwork | Unassigned
2 Oct 2027 | AM | SIG-BIRM27-022 | Press office fascia | Hall 2 | Hall 2 entrance | Registration | 3000 | 1000 | 1 | Freestanding |  | Awaiting artwork | Unassigned
2 Oct 2027 | PM | SIG-BIRM27-023 | Hall 1 big screen content loop | Hall 1 | Feature area | Digital screen | 3000 | 1000 | 1 | Digital |  | Draft | Unassigned
2 Oct 2027 | AM | SIG-BIRM27-024 | Wayfinding floor arrows | Hall 2 | Seminar theatre 2 | Floor vinyl | 3000 | 1000 | 1 | Floor |  | Draft | Unassigned
2 Oct 2027 | PM | SIG-BIRM27-025 | ToolMart seminar bunting | Hall 2 | Seminar theatre 2 | Seminar theatre | 3000 | 1000 | 1 | Freestanding |  | Draft | Unassigned
2 Oct 2027 | AM | SIG-BIRM27-026 | External car park totems | Hall 2 | External approach | External | 3000 | 1000 | 1 | Freestanding |  | Draft | Unassigned
2 Oct 2027 | PM | SIG-BIRM27-027 | Smoking area signage | Hall 2 | External approach | Foamex board | 3000 | 1000 | 1 | Wall mounted |  | Draft | Unassigned
2 Oct 2027 | AM | SIG-BIRM27-028 | First aid point signs | Hall 1 | Catering court | Foamex board | 3000 | 1000 | 1 | Wall mounted |  | Changes requested | Unassigned
2 Oct 2027 | PM | SIG-BIRM27-029 | BuildCo entrance feature cladding | Hall 1 | Main entrance | Entrance feature | 3000 | 1000 | 1 | Freestanding |  | In review | Unassigned
2 Oct 2027 | AM | SIG-BIRM27-030 | Recycling point signage | Hall 2 | Link corridor | Foamex board | 3000 | 1000 | 1 | Wall mounted |  | Draft | Unassigned
TBC |  | SIG-BIRM27-031 | E2E test sign 1789742365412 | Hall 1 | Registration | Foamex board | 1200 | 800 | 1 | Wall mounted |  | Awaiting artwork | Unassigned
TBC |  | SIG-BIRM27-032 | E2E test sign 1789742409349 | Hall 1 | Registration | Foamex board | 1200 | 800 | 1 | Wall mounted |  | Awaiting artwork | Unassigned
TBC |  | SIG-BIRM27-033 | E2E test sign 1789742782693 | Hall 1 | Registration | Foamex board | 1200 | 800 | 1 | Wall mounted |  | Awaiting artwork | Unassigned
TBC |  | SIG-BIRM27-034 | E2E test sign 1789743854785 | Hall 1 | Registration | Foamex board | 1200 | 800 | 1 | Wall mounted |  | Awaiting artwork | Unassigned
TBC |  | SIG-BIRM27-035 | E2E test sign 1789743908499 | Hall 1 | Registration | Foamex board | 1200 | 800 | 1 | Wall mounted |  | In review | Unassigned
TBC |  | SIG-BIRM27-036 | E2E test sign 1789746737063 | Hall 1 | Registration | Foamex board | 1200 | 800 | 1 | Wall mounted |  | In review | Unassigned
TBC |  | SIG-BIRM27-037 | E2E test sign 1789747154397 | Hall 1 | Registration | Foamex board | 1200 | 800 | 1 | Wall mounted |  | In review | Unassigned
TBC |  | SIG-BIRM27-038 | E2E test sign 1789748321968 | Hall 1 | Registration | Foamex board | 1200 | 800 | 1 | Wall mounted |  | In review | Unassigned

## Deliveries
Delivery date | Ref | Name | Hall | Qty | Supplier PO | Status