## Venue submission
Ref | Name | Hall | Location | Type | W (mm) | H (mm) | D (mm) | Qty | Weight (kg) | Fixing method | Material | Install date | Venue approval
SIG-BIRM27-001 | Main entrance arch banner | Hall 1 | Main entrance | Entrance feature | 3000 | 1000 |  | 1 |  | Freestanding | Tension fabric | 2 Oct 2027 | Waiting
SIG-BIRM27-003 | Aisle A hanging banner | Hall 1 | Central aisle A | Hanging banner | 3000 | 1000 |  | 1 |  | Rigged | Tension fabric | 2 Oct 2027 | Waiting
SIG-BIRM27-007 | Hall 2 entrance banner | Hall 2 | Hall 2 entrance | Hanging banner | 3000 | 1000 |  | 1 |  | Rigged | Tension fabric | 2 Oct 2027 | Pending
SIG-BIRM27-008 | Aisle B hanging banner | Hall 2 | Central aisle B | Aisle sign | 3000 | 1000 |  | 1 |  | Rigged | Tension fabric | 2 Oct 2027 | Approved 15 Sept 2026 (Nina at NEC)
SIG-BIRM27-011 | External approach flags | Hall 2 | External approach | External | 3000 | 1000 |  | 1 |  | Freestanding | Tension fabric | 2 Oct 2027 | Approved 15 Sept 2026 (Nina at NEC)
SIG-BIRM27-014 | Hall 1 aisle signs set | Hall 1 | Central aisle A | Aisle sign | 3000 | 1000 |  | 1 |  | Rigged | Tension fabric | 2 Oct 2027 | Approved 15 Sept 2026 (Nina at NEC)
SIG-BIRM27-017 | Gantry banner over aisle C | Hall 2 | Central aisle B | Hanging banner | 3000 | 1000 |  | 1 |  | Rigged | Tension fabric | 2 Oct 2027 | Waiting
SIG-BIRM27-019 | BuildCo banner — north hall | Hall 1 | Central aisle A | Hanging banner | 3000 | 1000 |  | 1 |  | Rigged | Tension fabric | 2 Oct 2027 | Waiting
SIG-BIRM27-026 | External car park totems | Hall 2 | External approach | External | 3000 | 1000 |  | 1 |  | Freestanding | Tension fabric | 2 Oct 2027 | Not yet submitted
SIG-BIRM27-029 | BuildCo entrance feature cladding | Hall 1 | Main entrance | Entrance feature | 3000 | 1000 |  | 1 |  | Freestanding | Tension fabric | 2 Oct 2027 | Approved 15 Sept 2026 (Nina at NEC)