## Summary
Ref | Name | Status | Type | Hall | Location | W (mm) | H (mm) | Qty | Material | Finish | Fixing | Sponsor | Supplier | Install | Estimate £ | Actual £ | PO | Delivered | Event Director sign-off | Installed | Marketing brand check | Ops technical check | Sent to print | Sponsor approval | Venue approval
SIG-BIRM27-001 | Main entrance arch banner | In review | Entrance feature | Hall 1 | Main entrance | 3000 | 1000 | 1 | Tension fabric | Matt | Freestanding | BuildCo | Big Print Co | 2 Oct 2027 PM | 12000 |  |  | Waiting | Waiting | Waiting | Pending | Waiting | Waiting | Pending | Waiting
SIG-BIRM27-002 | Registration desk fascia | In review | Registration | Hall 1 | Registration | 3000 | 1000 | 1 | Tension fabric | Matt | Freestanding |  | Big Print Co | 2 Oct 2027 AM | 1800 |  |  | Waiting |  | Waiting | Approved 14 Sept 2026, Marcus Marketing | Pending | Waiting
SIG-BIRM27-003 | Aisle A hanging banner | In review | Hanging banner | Hall 1 | Central aisle A | 3000 | 1000 | 1 | Tension fabric | Matt | Rigged | BuildCo | Big Print Co | 2 Oct 2027 PM | 2400 |  |  | Waiting |  | Waiting | Approved 7 Sept 2026, Marcus Marketing | Pending | Waiting | Approved 7 Sept 2026, Sara Sales | Waiting
SIG-BIRM27-004 | Seminar theatre 1 backdrop | In review | Seminar theatre | Hall 1 | Seminar theatre 1 | 3000 | 1000 | 1 | Tension fabric | Matt | Freestanding | ToolMart | Big Print Co | 2 Oct 2027 AM | 3200 |  |  | Waiting |  | Waiting | Pending | Waiting | Waiting | Pending
SIG-BIRM27-005 | Catering court floor vinyl | Changes requested | Floor vinyl | Hall 1 | Catering court | 3000 | 1000 | 1 | Tension fabric | Matt | Floor |  | Big Print Co | 2 Oct 2027 PM | 900 |  |  | Waiting |  | Waiting | Changes requested 14 Sept 2026, Marcus Marketing | Waiting | Waiting
SIG-BIRM27-006 | Feature area totem | In review | Feature area | Hall 1 | Feature area | 3000 | 1000 | 1 | Tension fabric | Matt | Freestanding |  | Big Print Co | 2 Oct 2027 AM | 8000 |  |  | Waiting | Pending | Waiting | Approved 7 Sept 2026, Marcus Marketing | Approved 7 Sept 2026, Olivia Ops | Waiting
SIG-BIRM27-007 | Hall 2 entrance banner | In review | Hanging banner | Hall 2 | Hall 2 entrance | 3000 | 1000 | 1 | Tension fabric | Matt | Rigged |  | Big Print Co | 2 Oct 2027 PM | 2100 |  |  | Waiting |  | Waiting | Approved 14 Sept 2026, Marcus Marketing | Approved 14 Sept 2026, Olivia Ops | Waiting |  | Pending
SIG-BIRM27-008 | Aisle B hanging banner | Approved | Aisle sign | Hall 2 | Central aisle B | 3000 | 1000 | 1 | Tension fabric | Matt | Rigged |  | Big Print Co | 2 Oct 2027 AM | 1500 |  |  | Waiting |  | Waiting | Approved 14 Sept 2026, Marcus Marketing | Approved 14 Sept 2026, Olivia Ops | Pending |  | Approved 14 Sept 2026, Nina at NEC
SIG-BIRM27-009 | Seminar theatre 2 entrance sign | Approved with conditions | Seminar theatre | Hall 2 | Seminar theatre 2 | 3000 | 1000 | 1 | Tension fabric | Matt | Freestanding | ToolMart | Big Print Co | 2 Oct 2027 PM | 2800 |  |  | Waiting |  | Waiting | Approved 14 Sept 2026, Marcus Marketing | Approved 14 Sept 2026, Olivia Ops | Pending | Approved with conditions 14 Sept 2026, Sara Sales
SIG-BIRM27-010 | Networking lounge fabric wall | In production | Fabric graphic | Hall 2 | Networking lounge | 3000 | 1000 | 1 | Tension fabric | Matt | Shell mounted |  | Big Print Co | 2 Oct 2027 AM | 3600 |  |  | Pending |  | Waiting | Approved 14 Sept 2026, Marcus Marketing | Approved 14 Sept 2026, Olivia Ops | Confirmed 14 Sept 2026, Petra at Big Print
SIG-BIRM27-011 | External approach flags | In production | External | Hall 2 | External approach | 3000 | 1000 | 1 | Tension fabric | Matt | Freestanding |  | Big Print Co | 2 Oct 2027 PM | 4200 |  |  | Pending |  | Waiting | Approved 14 Sept 2026, Marcus Marketing | Approved 14 Sept 2026, Olivia Ops | Confirmed 14 Sept 2026, Petra at Big Print |  | Approved 14 Sept 2026, Nina at NEC
SIG-BIRM27-012 | Link corridor wayfinding | Delivered | Foamex board | Hall 2 | Link corridor | 3000 | 1000 | 1 | Tension fabric | Matt | Wall mounted |  | Big Print Co | 2 Oct 2027 AM | 700 |  |  | Confirmed 14 Sept 2026, Petra at Big Print |  | Pending | Approved 14 Sept 2026, Marcus Marketing | Approved 14 Sept 2026, Olivia Ops | Confirmed 14 Sept 2026, Petra at Big Print
SIG-BIRM27-013 | Registration totem screens | Delivered | Digital screen | Hall 1 | Registration | 3000 | 1000 | 1 | Tension fabric | Matt | Digital |  | Screen Hire Ltd | 2 Oct 2027 PM | 5200 |  |  | Confirmed 14 Sept 2026, Petra at Big Print | Approved 14 Sept 2026, Dana Director | Pending | Approved 14 Sept 2026, Marcus Marketing | Approved 14 Sept 2026, Olivia Ops | Confirmed 14 Sept 2026, Petra at Big Print
SIG-BIRM27-014 | Hall 1 aisle signs set | Installed | Aisle sign | Hall 1 | Central aisle A | 3000 | 1000 | 1 | Tension fabric | Matt | Rigged |  | Big Print Co | 2 Oct 2027 AM | 3900 |  |  | Confirmed 14 Sept 2026, Petra at Big Print |  | Confirmed 14 Sept 2026, Olivia Ops | Approved 14 Sept 2026, Marcus Marketing | Approved 14 Sept 2026, Olivia Ops | Confirmed 14 Sept 2026, Petra at Big Print |  | Approved 14 Sept 2026, Nina at NEC
SIG-BIRM27-015 | Catering signage pack | Snagged | Foamex board | Hall 1 | Catering court | 3000 | 1000 | 1 | Tension fabric | Matt | Wall mounted |  | Big Print Co | 2 Oct 2027 PM | 1100 |  |  | Confirmed 14 Sept 2026, Petra at Big Print |  | Confirmed 14 Sept 2026, Olivia Ops | Approved 14 Sept 2026, Marcus Marketing | Approved 14 Sept 2026, Olivia Ops | Confirmed 14 Sept 2026, Petra at Big Print
SIG-BIRM27-016 | Sponsor wall Hall 1 | Closed | Feature area | Hall 1 | Feature area | 3000 | 1000 | 1 | Tension fabric | Matt | Freestanding | BuildCo | Big Print Co | 2 Oct 2027 AM | 2600 |  |  | Confirmed 14 Sept 2026, Petra at Big Print |  | Confirmed 14 Sept 2026, Olivia Ops | Approved 14 Sept 2026, Marcus Marketing | Approved 14 Sept 2026, Olivia Ops | Confirmed 14 Sept 2026, Petra at Big Print | Approved 14 Sept 2026, Sara Sales
SIG-BIRM27-017 | Gantry banner over aisle C | Rejected | Hanging banner | Hall 2 | Central aisle B | 3000 | 1000 | 1 | Tension fabric | Matt | Rigged |  | Big Print Co | 2 Oct 2027 PM | 2000 |  |  | Waiting |  | Waiting | Rejected 14 Sept 2026, Marcus Marketing | Waiting | Waiting |  | Waiting
SIG-BIRM27-018 | VIP lounge entrance sign | On hold | Fabric graphic | Hall 2 | Networking lounge | 3000 | 1000 | 1 | Tension fabric | Matt | Shell mounted |  | Big Print Co | 2 Oct 2027 AM | 1400 |  |  | Waiting |  | Waiting | Approved 14 Sept 2026, Marcus Marketing | Pending | Waiting
SIG-BIRM27-019 | BuildCo banner — north hall | In review | Hanging banner | Hall 1 | Central aisle A | 3000 | 1000 | 1 | Tension fabric | Matt | Rigged | BuildCo | Big Print Co | 2 Oct 2027 PM | 2400 |  |  | Waiting |  | Waiting | Pending | Waiting | Waiting | Pending | Waiting
SIG-BIRM27-020 | Organiser office door signs | Awaiting artwork | Foamex board | Hall 2 | Link corridor | 3000 | 1000 | 1 | Tension fabric | Matt | Wall mounted |  | Big Print Co | 2 Oct 2027 AM | 300
SIG-BIRM27-021 | Cloakroom signage | Awaiting artwork | Foamex board | Hall 1 | Registration | 3000 | 1000 | 1 | Tension fabric | Matt | Wall mounted |  | Big Print Co | 2 Oct 2027 PM | 250
SIG-BIRM27-022 | Press office fascia | Awaiting artwork | Registration | Hall 2 | Hall 2 entrance | 3000 | 1000 | 1 | Tension fabric | Matt | Freestanding |  |  | 2 Oct 2027 AM | 800
SIG-BIRM27-023 | Hall 1 big screen content loop | Draft | Digital screen | Hall 1 | Feature area | 3000 | 1000 | 1 | Tension fabric | Matt | Digital |  | Screen Hire Ltd | 2 Oct 2027 PM | 6000
SIG-BIRM27-024 | Wayfinding floor arrows | Draft | Floor vinyl | Hall 2 | Seminar theatre 2 | 3000 | 1000 | 1 | Tension fabric | Matt | Floor |  |  | 2 Oct 2027 AM | 450
SIG-BIRM27-025 | ToolMart seminar bunting | Draft | Seminar theatre | Hall 2 | Seminar theatre 2 | 3000 | 1000 | 1 | Tension fabric | Matt | Freestanding | ToolMart |  | 2 Oct 2027 PM | 600
SIG-BIRM27-026 | External car park totems | Draft | External | Hall 2 | External approach | 3000 | 1000 | 1 | Tension fabric | Matt | Freestanding |  |  | 2 Oct 2027 AM | 5400
SIG-BIRM27-027 | Smoking area signage | Draft | Foamex board | Hall 2 | External approach | 3000 | 1000 | 1 | Tension fabric | Matt | Wall mounted |  |  | 2 Oct 2027 PM | 150
SIG-BIRM27-028 | First aid point signs | Changes requested | Foamex board | Hall 1 | Catering court | 3000 | 1000 | 1 | Tension fabric | Matt | Wall mounted |  | Big Print Co | 2 Oct 2027 AM | 320 |  |  | Waiting |  | Waiting | Changes requested 14 Sept 2026, Marcus Marketing | Waiting | Waiting
SIG-BIRM27-029 | BuildCo entrance feature cladding | In review | Entrance feature | Hall 1 | Main entrance | 3000 | 1000 | 1 | Tension fabric | Matt | Freestanding | BuildCo | Big Print Co | 2 Oct 2027 PM | 15000 |  |  | Waiting | Pending | Waiting | Approved 14 Sept 2026, Marcus Marketing | Approved 14 Sept 2026, Olivia Ops | Waiting | Approved 14 Sept 2026, Sara Sales | Approved 14 Sept 2026, Nina at NEC
SIG-BIRM27-030 | Recycling point signage | Draft | Foamex board | Hall 2 | Link corridor | 3000 | 1000 | 1 | Tension fabric | Matt | Wall mounted |  |  | 2 Oct 2027 AM | 200

## Hall 1
Ref | Name | Status | Type | Hall | Location | W (mm) | H (mm) | Qty | Material | Finish | Fixing | Sponsor | Supplier | Install | Estimate £ | Actual £ | PO | Delivered | Event Director sign-off | Installed | Marketing brand check | Ops technical check | Sent to print | Sponsor approval | Venue approval
SIG-BIRM27-001 | Main entrance arch banner | In review | Entrance feature | Hall 1 | Main entrance | 3000 | 1000 | 1 | Tension fabric | Matt | Freestanding | BuildCo | Big Print Co | 2 Oct 2027 PM | 12000 |  |  | Waiting | Waiting | Waiting | Pending | Waiting | Waiting | Pending | Waiting
SIG-BIRM27-002 | Registration desk fascia | In review | Registration | Hall 1 | Registration | 3000 | 1000 | 1 | Tension fabric | Matt | Freestanding |  | Big Print Co | 2 Oct 2027 AM | 1800 |  |  | Waiting |  | Waiting | Approved 14 Sept 2026, Marcus Marketing | Pending | Waiting
SIG-BIRM27-003 | Aisle A hanging banner | In review | Hanging banner | Hall 1 | Central aisle A | 3000 | 1000 | 1 | Tension fabric | Matt | Rigged | BuildCo | Big Print Co | 2 Oct 2027 PM | 2400 |  |  | Waiting |  | Waiting | Approved 7 Sept 2026, Marcus Marketing | Pending | Waiting | Approved 7 Sept 2026, Sara Sales | Waiting
SIG-BIRM27-004 | Seminar theatre 1 backdrop | In review | Seminar theatre | Hall 1 | Seminar theatre 1 | 3000 | 1000 | 1 | Tension fabric | Matt | Freestanding | ToolMart | Big Print Co | 2 Oct 2027 AM | 3200 |  |  | Waiting |  | Waiting | Pending | Waiting | Waiting | Pending
SIG-BIRM27-005 | Catering court floor vinyl | Changes requested | Floor vinyl | Hall 1 | Catering court | 3000 | 1000 | 1 | Tension fabric | Matt | Floor |  | Big Print Co | 2 Oct 2027 PM | 900 |  |  | Waiting |  | Waiting | Changes requested 14 Sept 2026, Marcus Marketing | Waiting | Waiting
SIG-BIRM27-006 | Feature area totem | In review | Feature area | Hall 1 | Feature area | 3000 | 1000 | 1 | Tension fabric | Matt | Freestanding |  | Big Print Co | 2 Oct 2027 AM | 8000 |  |  | Waiting | Pending | Waiting | Approved 7 Sept 2026, Marcus Marketing | Approved 7 Sept 2026, Olivia Ops | Waiting
SIG-BIRM27-013 | Registration totem screens | Delivered | Digital screen | Hall 1 | Registration | 3000 | 1000 | 1 | Tension fabric | Matt | Digital |  | Screen Hire Ltd | 2 Oct 2027 PM | 5200 |  |  | Confirmed 14 Sept 2026, Petra at Big Print | Approved 14 Sept 2026, Dana Director | Pending | Approved 14 Sept 2026, Marcus Marketing | Approved 14 Sept 2026, Olivia Ops | Confirmed 14 Sept 2026, Petra at Big Print
SIG-BIRM27-014 | Hall 1 aisle signs set | Installed | Aisle sign | Hall 1 | Central aisle A | 3000 | 1000 | 1 | Tension fabric | Matt | Rigged |  | Big Print Co | 2 Oct 2027 AM | 3900 |  |  | Confirmed 14 Sept 2026, Petra at Big Print |  | Confirmed 14 Sept 2026, Olivia Ops | Approved 14 Sept 2026, Marcus Marketing | Approved 14 Sept 2026, Olivia Ops | Confirmed 14 Sept 2026, Petra at Big Print |  | Approved 14 Sept 2026, Nina at NEC
SIG-BIRM27-015 | Catering signage pack | Snagged | Foamex board | Hall 1 | Catering court | 3000 | 1000 | 1 | Tension fabric | Matt | Wall mounted |  | Big Print Co | 2 Oct 2027 PM | 1100 |  |  | Confirmed 14 Sept 2026, Petra at Big Print |  | Confirmed 14 Sept 2026, Olivia Ops | Approved 14 Sept 2026, Marcus Marketing | Approved 14 Sept 2026, Olivia Ops | Confirmed 14 Sept 2026, Petra at Big Print
SIG-BIRM27-016 | Sponsor wall Hall 1 | Closed | Feature area | Hall 1 | Feature area | 3000 | 1000 | 1 | Tension fabric | Matt | Freestanding | BuildCo | Big Print Co | 2 Oct 2027 AM | 2600 |  |  | Confirmed 14 Sept 2026, Petra at Big Print |  | Confirmed 14 Sept 2026, Olivia Ops | Approved 14 Sept 2026, Marcus Marketing | Approved 14 Sept 2026, Olivia Ops | Confirmed 14 Sept 2026, Petra at Big Print | Approved 14 Sept 2026, Sara Sales
SIG-BIRM27-019 | BuildCo banner — north hall | In review | Hanging banner | Hall 1 | Central aisle A | 3000 | 1000 | 1 | Tension fabric | Matt | Rigged | BuildCo | Big Print Co | 2 Oct 2027 PM | 2400 |  |  | Waiting |  | Waiting | Pending | Waiting | Waiting | Pending | Waiting
SIG-BIRM27-021 | Cloakroom signage | Awaiting artwork | Foamex board | Hall 1 | Registration | 3000 | 1000 | 1 | Tension fabric | Matt | Wall mounted |  | Big Print Co | 2 Oct 2027 PM | 250
SIG-BIRM27-023 | Hall 1 big screen content loop | Draft | Digital screen | Hall 1 | Feature area | 3000 | 1000 | 1 | Tension fabric | Matt | Digital |  | Screen Hire Ltd | 2 Oct 2027 PM | 6000
SIG-BIRM27-028 | First aid point signs | Changes requested | Foamex board | Hall 1 | Catering court | 3000 | 1000 | 1 | Tension fabric | Matt | Wall mounted |  | Big Print Co | 2 Oct 2027 AM | 320 |  |  | Waiting |  | Waiting | Changes requested 14 Sept 2026, Marcus Marketing | Waiting | Waiting
SIG-BIRM27-029 | BuildCo entrance feature cladding | In review | Entrance feature | Hall 1 | Main entrance | 3000 | 1000 | 1 | Tension fabric | Matt | Freestanding | BuildCo | Big Print Co | 2 Oct 2027 PM | 15000 |  |  | Waiting | Pending | Waiting | Approved 14 Sept 2026, Marcus Marketing | Approved 14 Sept 2026, Olivia Ops | Waiting | Approved 14 Sept 2026, Sara Sales | Approved 14 Sept 2026, Nina at NEC

## Hall 2
Ref | Name | Status | Type | Hall | Location | W (mm) | H (mm) | Qty | Material | Finish | Fixing | Sponsor | Supplier | Install | Estimate £ | Actual £ | PO | Delivered | Event Director sign-off | Installed | Marketing brand check | Ops technical check | Sent to print | Sponsor approval | Venue approval
SIG-BIRM27-007 | Hall 2 entrance banner | In review | Hanging banner | Hall 2 | Hall 2 entrance | 3000 | 1000 | 1 | Tension fabric | Matt | Rigged |  | Big Print Co | 2 Oct 2027 PM | 2100 |  |  | Waiting |  | Waiting | Approved 14 Sept 2026, Marcus Marketing | Approved 14 Sept 2026, Olivia Ops | Waiting |  | Pending
SIG-BIRM27-008 | Aisle B hanging banner | Approved | Aisle sign | Hall 2 | Central aisle B | 3000 | 1000 | 1 | Tension fabric | Matt | Rigged |  | Big Print Co | 2 Oct 2027 AM | 1500 |  |  | Waiting |  | Waiting | Approved 14 Sept 2026, Marcus Marketing | Approved 14 Sept 2026, Olivia Ops | Pending |  | Approved 14 Sept 2026, Nina at NEC
SIG-BIRM27-009 | Seminar theatre 2 entrance sign | Approved with conditions | Seminar theatre | Hall 2 | Seminar theatre 2 | 3000 | 1000 | 1 | Tension fabric | Matt | Freestanding | ToolMart | Big Print Co | 2 Oct 2027 PM | 2800 |  |  | Waiting |  | Waiting | Approved 14 Sept 2026, Marcus Marketing | Approved 14 Sept 2026, Olivia Ops | Pending | Approved with conditions 14 Sept 2026, Sara Sales
SIG-BIRM27-010 | Networking lounge fabric wall | In production | Fabric graphic | Hall 2 | Networking lounge | 3000 | 1000 | 1 | Tension fabric | Matt | Shell mounted |  | Big Print Co | 2 Oct 2027 AM | 3600 |  |  | Pending |  | Waiting | Approved 14 Sept 2026, Marcus Marketing | Approved 14 Sept 2026, Olivia Ops | Confirmed 14 Sept 2026, Petra at Big Print
SIG-BIRM27-011 | External approach flags | In production | External | Hall 2 | External approach | 3000 | 1000 | 1 | Tension fabric | Matt | Freestanding |  | Big Print Co | 2 Oct 2027 PM | 4200 |  |  | Pending |  | Waiting | Approved 14 Sept 2026, Marcus Marketing | Approved 14 Sept 2026, Olivia Ops | Confirmed 14 Sept 2026, Petra at Big Print |  | Approved 14 Sept 2026, Nina at NEC
SIG-BIRM27-012 | Link corridor wayfinding | Delivered | Foamex board | Hall 2 | Link corridor | 3000 | 1000 | 1 | Tension fabric | Matt | Wall mounted |  | Big Print Co | 2 Oct 2027 AM | 700 |  |  | Confirmed 14 Sept 2026, Petra at Big Print |  | Pending | Approved 14 Sept 2026, Marcus Marketing | Approved 14 Sept 2026, Olivia Ops | Confirmed 14 Sept 2026, Petra at Big Print
SIG-BIRM27-017 | Gantry banner over aisle C | Rejected | Hanging banner | Hall 2 | Central aisle B | 3000 | 1000 | 1 | Tension fabric | Matt | Rigged |  | Big Print Co | 2 Oct 2027 PM | 2000 |  |  | Waiting |  | Waiting | Rejected 14 Sept 2026, Marcus Marketing | Waiting | Waiting |  | Waiting
SIG-BIRM27-018 | VIP lounge entrance sign | On hold | Fabric graphic | Hall 2 | Networking lounge | 3000 | 1000 | 1 | Tension fabric | Matt | Shell mounted |  | Big Print Co | 2 Oct 2027 AM | 1400 |  |  | Waiting |  | Waiting | Approved 14 Sept 2026, Marcus Marketing | Pending | Waiting
SIG-BIRM27-020 | Organiser office door signs | Awaiting artwork | Foamex board | Hall 2 | Link corridor | 3000 | 1000 | 1 | Tension fabric | Matt | Wall mounted |  | Big Print Co | 2 Oct 2027 AM | 300
SIG-BIRM27-022 | Press office fascia | Awaiting artwork | Registration | Hall 2 | Hall 2 entrance | 3000 | 1000 | 1 | Tension fabric | Matt | Freestanding |  |  | 2 Oct 2027 AM | 800
SIG-BIRM27-024 | Wayfinding floor arrows | Draft | Floor vinyl | Hall 2 | Seminar theatre 2 | 3000 | 1000 | 1 | Tension fabric | Matt | Floor |  |  | 2 Oct 2027 AM | 450
SIG-BIRM27-025 | ToolMart seminar bunting | Draft | Seminar theatre | Hall 2 | Seminar theatre 2 | 3000 | 1000 | 1 | Tension fabric | Matt | Freestanding | ToolMart |  | 2 Oct 2027 PM | 600
SIG-BIRM27-026 | External car park totems | Draft | External | Hall 2 | External approach | 3000 | 1000 | 1 | Tension fabric | Matt | Freestanding |  |  | 2 Oct 2027 AM | 5400
SIG-BIRM27-027 | Smoking area signage | Draft | Foamex board | Hall 2 | External approach | 3000 | 1000 | 1 | Tension fabric | Matt | Wall mounted |  |  | 2 Oct 2027 PM | 150
SIG-BIRM27-030 | Recycling point signage | Draft | Foamex board | Hall 2 | Link corridor | 3000 | 1000 | 1 | Tension fabric | Matt | Wall mounted |  |  | 2 Oct 2027 AM | 200