## Stand approvals
Stand | Exhibitor | Type | Contractor | Status | Complex | Max height (mm) | Outcome | Conditions | Approvals
A10 | Exhibitor Co | Space only | Stand Builders Ltd | In review | Yes | 5200 |  |  | Ops completeness and rules check: Approved 13 Sept 2026 (Olivia Ops)
A20 | SteelFrame Systems | Space only | Custom Stands Co | In review | No | 3400
A30 | BrickWorks UK | Space only | Stand Builders Ltd | Changes requested | No | 3800 |  |  | Ops completeness and rules check: Changes requested 13 Sept 2026 (Olivia Ops)
B10 | Timber Trade Ltd | Space only | Custom Stands Co | Approved with conditions | No | 3000 | Approved with conditions | Handrail detail to be verified onsite before opening. | Ops completeness and rules check: Approved 13 Sept 2026 (Olivia Ops); H&S review (RAMS, insurance): Approved 13 Sept 2026 (Harri Safety); Venue approval: Approved 13 Sept 2026 (Nina at NEC); Ops final outcome: Approved with conditions 13 Sept 2026 (Olivia Ops)
B20 | GlassTech | Space only | Stand Builders Ltd | Approved | No | 2900 | Approved |  | Ops completeness and rules check: Approved 13 Sept 2026 (Olivia Ops); H&S review (RAMS, insurance): Approved 13 Sept 2026 (Harri Safety); Venue approval: Approved 13 Sept 2026 (Nina at NEC); Ops final outcome: Approved 13 Sept 2026 (Olivia Ops)
B30 | Insulate Pro | Space only | Custom Stands Co | Not submitted | No
C10 | RoofRight | Space only | Stand Builders Ltd | Not submitted | No
C20 | PlantHire Direct | Space only | Custom Stands Co | Not submitted | No
D10 | SafetyFirst PPE | Shell |  | Not submitted | No
D20 | ToolMart Retail | Shell |  | Not submitted | No
D30 | EcoBuild Materials | Shell |  | Not submitted | No
D40 | SiteWise Software | Shell |  | Not submitted | No